## LMS nrbjob bug report
Project Name |  |  | Environment
Tester's Name |  | kawser kabir | Reviewed By
Date Tested |  | 29/05/24 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment | comment
1 | Forgot password? | The login form is incorrect. | login form should change like actual login form | Click->Login Now button Click->Forgot password button Click->Login button | Bug | low | medium |  |  | image | DONE
2 | Forgot password? | The Register form is incorrect. | Register form should change like actual Register form | Click->Login Now button Click->Forgot password button Click->Register button | Bug | high | critical |  |  | image | DONE
3 | Enroll courses | Select 1st year training at DU but price not showing | After select 1st yr traing at Du price not showing | Click->Courses Click->offline courses click->Du (Dhaka university) Click ->1st year training | Bug | high | critical |  |  | image | DONE
4 | Enroll form enrollment form | Total Payable Price show 0 | after select courses enrollment form Total Payable Price show 0 | Click->Courses Click->offline courses click->Du (Dhaka university) Click ->1st year training click-> Enroll courses | Bug | high | critical |  |  | image | DONE
5 | Course Enroll form | "upload ur id" not uploading | course enrollment form recomened pic size doesnot excepted | click->courses click->offline training click->university program select->subject click-enroll courses | Bug | medium | major |  |  | image | DONE
6 | Course Enroll form | "Upload You Photo" not uploading | course enrollment form recomened pic size doesnot excepted | click->courses click->offline training click->university program select->subject click-enroll courses | Bug | medium | major |  |  | image | DONE
7 | enroll message | wrong place | after enroll courses we get message but we have to get message after enrollment form submition | click->courses click->offline training click->university program select->subject click-enroll courses | Bug | low | minor |  |  | image | DONE
8 | Course Enrollment list | Action button not working | after clicking action button its not working | click->profile click->enroll courses click->action button | Bug | high | critical |  |  | image | DONE
9 | Course Enrollment list | lesson number not working | after clicking lesson number its not working | click->profile click->enroll courses click->lesson number | Bug | high | critical |  |  | image | DONE
10 | Student profile update | profile not uplading | recomened pic size doesnot excepted | click->profile click->profile update | Bug | medium | major |  |  | image | DONE
11 | online package discount | text error | online package discount text error | click->courses click->online training click->enroll courses | Bug | low | minor |  |  | image | DONE
12 | course enrollment offline | enroll course button not working | after click enroll courses button it not working | "click->courses click->offline training click->university program select->subject click-enroll courses" | Bug | high | critical |  |  | image | DONE
13 | Assignment | Assignment video link not found | assignment link not found in assignment section | click->profile click ->any courses click->assignment | Bug | low | minor |  |  | image | DONE
14 | meet our instructors (link) | profile link not working | after click instructor profile link not working | click->about us click->instructor | Bug | low | minor |  |  |  | DONE
15 | course details-> instructor (link) | profile link not working | after click instructor profile link not working | click->courses click->offline training click->university program click-course details click->instructor click->instructor profile name | Bug | low | minor |  |  | image | DONE
16 | instructor social media link-> facebook , X , Youtube , linkin | social media link not working | after click social media icon it goes to there social midea profile | click->instructors click ->any instructor name click social media link | Bug | low | minor |  |  | image | DONE
17 | course details | instructor review option delete | review option delet form course details section | click->offline training click->any university click->course details | Bug | low | minor |  |  | image | DONE
18 | password need to between 8 tp 20 | password escept up to 20 carecter | password must be 8-20 carecter | click->sign up | Bug | low | minor |  |  | image | DONE
19 | instructor profile update | text modification | text error in youtube url fild | click->profile click->profile update | Bug | low | minor |  |  | image | DONE
20 | cheak all -> perches all | text modification | cheak all replase with perches all | click->courses click->online/offline training click->any university | Bug | low | minor |  |  | image | DONE
21 | instructor-> enroll courses need to change Facilitate courses | text modification | enroll courses need to change Facilitate courses | click->instructor profile | Bug | low | minor |  |  | image | DONE
22 | instructor dashbord | total student count worng | fix the total student count | click->profile click->total student number | Bug | high | critical |  |  | image | DONE
23 | instructor profile update -> 120*120 px | "Upload You Photo" not uploading | recomened pic size doesnot excepted | click->profile click->profile update | Bug | high | critical |  |  | image | DONE
24 | admin dashbord | student count not working | after click student number it goes to student list | click->profile click->student | Bug | high | critical |  |  | image | DONE
25 | admin dashbord-> teacher count not working | teacher count not working | after click teacher number it goes to teacher list | click->profile click->teacher | Bug | high | critical |  |  | image | DONE
26 | admin dashbord-> user admin count not working | admin count not working | after click admin number it goes to admin list | click->profile click->admin | Bug | high | critical |  |  | image | DONE
27 | account -> need to user name and picture | user name and pic not view | user pic and name always show | click->user profile | Bug | high | critical |  |  | image | DONE
28 | admin->event-> creat event should be update event | worng text in event update | creat event should be update event | click->profile click->activity management click->event click->action | Bug | medium | major |  |  | image | DONE
29 | admin ->event ->delete option not working | event delete optin not working | after click event delete oftion ti should be delete | click->profile click->activity management click->event click->delete | Bug | medium | major |  |  | image | DONE
30 | student/instructor->event pagination bar not working | event pagination bar not working | after click pagination bar it should be change | click->event | Bug | medium | major |  |  | image | DONE
32 | announcement->admin sent show worng time | worng time show | after send message worng time show | click->notification button click->message view | Bug | high | critical |  |  | image | DONE
33 | adit quze | close button not working | after click close button it should be closed | click->course click->view button click->manage quze click->adit quze | [5 empty] | image | DONE
34 | assignment need to feedback option ->instructor | assignment no feedback option | assignment need to feedback option | click->course click->enroll student click->action | Bug | high | critical |  |  | image | DONE
35 | perchase history ->student details->academic year not showing | academic year not showing | acedemic year must show in the student details | click->purchase histories click->view button | Bug | medium | major |  |  | image | DONE
36 | admin->student list | student pic not view | after click student id view student pic | click->profile click->student click->student id | Bug | high | critical |  |  | image | DONE
37 | student list | student pic not view | after click student id view student pic | click->profile click->total student number click->student id | Bug | medium | major |  |  | image | DONE
39 | announcement | message allignment not ok | after sent message the message alligment broke | click->profile click->activity click->announcement | Bug | medium | major |  |  | image | DONE
40 | Admin-> enrollment list->user details | academic year not showing | acedemic year must show in the student details | click->profile click->enrollment list click->user details | Bug | medium | major |  |  | image | DONE
41 | offline class list | offline class list text error | live class list it should beoffline class list | click->profile click->enroll courses click->action button | Bug | medium | major |  |  | image | DONE
42 | admin->modiule close button,view lesson close button, assignment close button | close button not working | after click close button it should be closed | click->course click->view button click->manage quze click->adit quze | Bug | medium | major |  |  | image | DONE
43 | instructor->modiule close button,view lesson close button, assignment close button | close button not working | after click close button it should be closed | click->course click->view button click->manage quze click->adit quze | Bug | medium | major |  |  | image | DONE
44 | instructor profile update | youtube URL text error | carrection the youtube URL | click->profile click->instructor click->adit | Bug | medium | major |  |  | image | DONE

## Sheet2
Improvement | High | Critical
Improvement | High | Critical
Bug | High | Critical
Bug | High | Critical